## Tester July
Bank Syariah Indonesia IT-Tester Daily Activity Reports
PT. Aplic Digital Teknologi
| Nama Tester/Programmer |  |  | Harry Setiawan
No | Tanggal | Jam |  | Project | Nama CR & No Dev | Status CR | Script All |  |  |  | Daily
|  | Masuk | Pulang |  |  | (SIT/UAT) | Total | Pass | Failed | Sisa | Execute
1 | 2022-08-15 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress |  |  |  | 0 | Scripting manual menu Profile & mengambil laptop di APL
2 | 2022-08-16 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 139 | 20 | 0 | 119 | Belajar struktur standarisasi dari scripting
3 | 2022-08-17 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 139 | 40 | 0 | 99 | Running & Scripting automation epic profile - change profil pic - positive
4 | 2022-08-18 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 139 | 40 | 0 | 99 | Running & Scripting automation epic profile - change profil pic - positive
5 | 2022-08-19 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 139 | 16 | 0 | 123 | Running & Scripting automation epic profile - change profil pic - negative
6 | 2022-08-20 | 9:00 | 18:00 | Sabtu
7 | 2022-08-21 | 9:00 | 18:00 | Minggu
8 | 2022-08-22 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 139 | 16 | 0 | 123 | Running & Scripting automation epic profile - change profil pic - negative
9 | 2022-08-23 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 139 | 53 | 0 | 86 | Running & Scripting automation epic profile - change email - positive
10 | 2022-08-24 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 139 | 16 | 1 | 122 | Running & Scripting automation epic profile - change email - negative
11 | 2022-08-25 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 54 | 23 | 0 | 31 | Running & Scripting automation epic berbagi - thr yatim - negative
12 | 2022-08-26 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 54 | 29 | 1 | 24 | Running & Scripting automation epic berbagi - thr yatim - positive
13 | 2022-08-27 | 9:00 | 18:00 | Sabtu
14 | 2022-08-28 | 9:00 | 18:00 | Minggu
15 | 2022-08-29 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 54 | 23 | 1 | 30 | Running & Scripting automation epic berbagi - thr yatim - negative
16 | 2022-08-30 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 124 | 58 | 6 | 60 | Running & Scripting automation epic bayar beli - car premi reguler - positive
17 | 2022-08-31 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 124 | 58 | 6 | 60 | Running & Scripting automation epic bayar beli - car premi reguler - positive
|  | Mengetahui, |  |  | Review by, | [5 empty] | Menyetujui,
|  | Harry Setiawan |  |  | Ruben Mikhael Hutabarat | [5 empty] | Christian Adi Sucipto
|  | Tester PT. Aplic Digital Teknologi |  |  | Performance Lead Engineer | [5 empty] | Departement Head IDG BSI