## Tester July
Bank Syariah Indonesia IT-Tester Daily Activity Reports
PT. Aplic Digital Teknologi
| Nama Tester/Programmer |  |  | Harry Setiawan
No | Tanggal | Jam |  | Project | Nama CR & No Dev | Status CR | Script All |  |  |  | Daily
|  | Masuk | Pulang |  |  | (SIT/UAT) | Total | Pass | Failed | Sisa | Execute
1 | 2022-10-01 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 3461 | 178 | 12 | 3271 | Regresi 150 pulsa telkomsel, indosat, xl, smartfren, tri. Regresi Paket data telkomsel
2 | 2022-10-02 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 3271 | 183 | 19 | 3069 | Regresi 150 change profile pic, delete profil pic, paket data (indosat, xl, smartfren, tri)
3 | 2022-10-03 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 3069 | 117 | 33 | 2919 | Regresi 150 bpjs pu, bpjs bpu, change email, bpjs kesehatan
4 | 2022-10-04 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 2919 | 150 | 12 | 2757 | Scripting kitabisa, dompet dhuafa, rumah zakat indonesia
5 | 2022-10-05 | 9:00 | 18:00 | Sabtu
6 | 2022-10-06 | 9:00 | 18:00 | Minggu
7 | 2022-10-07 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 2757 | 178 | 26 | 2553 | Regresi 153 pulsa telkomsel, indosat, xl, smartfren, tri. Regresi Paket data telkomsel
8 | 2022-10-08 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 2553 | 164 | 22 | 2367 | Regresi 153 pulsa telkomsel, indosat, xl, smartfren, tri. Regresi Paket data telkomsel
9 | 2022-10-09 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 2367 | 95 | 19 | 2253 | Regresi 156 change profile pic, delete profil pic, paket data (indosat, xl, smartfren, tri)
10 | 2022-10-10 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 2253 | 123 | 15 | 2115 | Regresi 156 bpjs pu, bpjs bpu, change email, bpjs kesehatan
11 | 2022-10-11 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 2115 | 138 | 8 | 1969 | Scripting kitabisa, dompet dhuafa, rumah zakat indonesia
12 | 2022-10-12 | 9:00 | 18:00 | Sabtu
13 | 2022-10-13 | 9:00 | 18:00 | Minggu
14 | 2022-10-14 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 1969 | 54 | 3 | 1912 | Scripting pajak/cukai/sbn/paspor, reinquiry mpn
15 | 2022-10-15 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 1912 | 167 | 34 | 1711 | Regresi 156 change profile pic, delete profil pic, change email, bpjs kesehatan, pulsa telkomsel, indosat, xl, smartfren, tri
16 | 2022-10-16 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 1711 | 210 | 27 | 1474 | Regresi 162 pulsa telkomsel, indosat, xl, smartfren, tri. Regresi Paket data telkomsel
17 | 2022-10-17 | 9:00 | 18:00 | BSI New CMS | Development Script Automation | SIT Progress | 387 | 20 | 69 | 298 | Scripting Payroll Multiservice
18 | 2022-10-18 | 9:00 | 18:00 | BSI New CMS | Development Script Automation | SIT Progress | 298 | 28 | 63 | 207 | Scripting Payroll Multiservice
19 | 2022-10-19 | 9:00 | 18:00 | Sabtu
20 | 2022-10-20 | 9:00 | 18:00 | Minggu
21 | 2022-10-21 | 9:00 | 18:00 | BSI New CMS | Development Script Automation | SIT Progress | 207 | 38 | 20 | 149 | Scripting Payroll Multiservice
22 | 2022-10-22 | 9:00 | 18:00 | BSI New CMS | Development Script Automation | SIT Progress | 149 | 67 | 7 | 75 | Scripting Payroll Multiservice
23 | 2022-10-23 | 9:00 | 18:00 | BSI SuperApp | Meeting JPA | SIT Progress | 75 | 72 | 3 | 0 | Meeting BPJS & PLN dengan JPA
24 | 2022-10-24 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 1474 | 241 | 30 | 1203 | Regresi 171 & 172 pulsa telkomsel, indosat, xl, smartfren, tri. Regresi Paket data telkomsel
25 | 2022-10-25 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 1203 | 283 | 41 | 879 | Regresi 172 change profile pic, delete profil pic, paket data (indosat, xl, smartfren, tri)
26 | 2022-10-26 | 9:00 | 18:00 | Sabtu
27 | 2022-10-27 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 879 | 231 | 12 | 636 | Regresi 174 & 175 pulsa telkomsel, indosat, xl, smartfren, tri. Regresi Paket data telkomsel
28 | 2022-10-28 | 9:00 | 22:30 | BSI SuperApp | Development Script Automation | SIT Progress | 636 | 283 | 26 | 327 | Regresi 176 & 177 pulsa telkomsel, indosat, xl, smartfren, tri. Regresi Paket data telkomsel
29 | 2022-10-29 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 327 | 174 | 19 | 134 | Regresi 177 change profile pic, delete profil pic, paket data (indosat, xl, smartfren, tri)
30 | 2022-10-30 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 134 | 94 | 9 | 31 | Regresi 177 bpjs pu, bpjs bpu, change email, bpjs kesehatan
31 | 2022-10-31 | 9:00 | 18:00 | BSI SuperApp | Development Script Automation | SIT Progress | 31 | 27 | 4 | 0 | Scripting kitabisa, dompet dhuafa, rumah zakat indonesia
|  | Mengetahui, |  |  | Review by, | [5 empty] | Menyetujui,
|  | Harry Setiawan |  |  | Ruben Mikhael Hutabarat | [5 empty] | Christian Adi Sucipto
|  | Tester PT. Aplic Digital Teknologi |  |  | Performance Lead Engineer | [5 empty] | Departement Head IDG BSI